Newcastle Safeguarding Adults Board Strategic Annual Plan 2025-26

“Ensuring Newcastle is an increasingly safer city for adults at risk of abuse or neglect.”

The Care Act (2014) requires all Safeguarding Adult Boards to produce and publish a Strategic Annual Plan.

The Newcastle Safeguarding Adults Board (NSAB) Strategic Annual Plan provides information on specific objectives, supporting actions and target timescales required to deliver the Board’s vision and priorities. It sets out how the NSAB seeks to prevent abuse and neglect and how the NSAB will protect people with care and support needs who are or may be at risk. We work with people to understand what being safe means to them as well as with our partners on the best way to achieve this. We concentrate on improving people’s lives while protecting their right to live in safety, free from bullying, harassment, abuse, discrimination, avoidable harm and neglect. We make sure we share concerns quickly and appropriately.

The Strategic Annual Plan is informed by a number of different sources including:

- Legislation, specifically the requirements of the Care Act (2014);

- Performance information and data analysis;

- Learning from Safeguarding Adult Reviews and multi-agency audits;

- Priorities emerging form joint work with other multi-agency partnerships e.g. Newcastle Safeguarding Children’s Partnership (NSCP) and Safe Newcastle

- Learning from all partner agency experiences, including responses to their self-assessments

- Consultation with partners, the public and practitioners.

- CQC Quality Statement for local authority assessments

The Strategic Annual Plan attempts to address weaknesses and respond to opportunities that have been identified.  Progress in relation to the plan will be reviewed at each NSAB meeting. A Red Amber Green (RAG) rating is used to assess progress in relation to each action area. The following index indicates how the rating is decided:

| # Status Rating |  |
| --- | --- |
| # Green | # Action on track and progressing to plan, no problems that will impact on schedule. No action required from NSAB. |
| # Amber | # Some problems and or delays with the action but expected to recover. Highlighted to inform NSAB, to be monitored and reviewed |
| # Red | # Major problems and issues threatening the action, behind schedule and not expected to recover. Requires intervention from NSAB |
| # Complete | # Action fully completed |

Some action areas take longer than a year to conclude, this years Strategic Annual Plan includes a number of actions carried forward from the previous year.

The NSAB works closely with other partnerships and organisations to achieve and support objectives that keep adults with care and support needs safe in Newcastle. The Strategic Annual Plan identifies which actions the Board leads on, and which it contributes to and influences.

Glossary

| ADASS | Association of Directors of Adult Social Services |
| --- | --- |
| CQC | Care Quality Commission |
| CNTW | Cumbria, Northumberland, Tyne and Wear NHS Foundation Trust |
| CPD | Continuing Professional Development |
| CSPR | Child Safeguarding Practice Review |
| DASS | Director of Adult Social Services |
| DHR | Domestic Homicide Review (sometimes referred to as a DARDR – Domestic Abuse Related Death Review) |
| EMNA | Ethnic Minority Needs Assessment |
| HAREF | Network to improve health equality for ethnically marginalised communities (delivered by Connected Voice) |
| IPC | Improving Practice Committee |
| JSNA | Joint Strategic Needs Assessment |
| LA | Local Authority |
| LGA | Local Government Association |
| MARM | Multi-Agency Risk Management |
| MASH | Multi-Agency Safeguarding Hub |
| MCA | Mental Capacity Act |
| MSP | Making Safeguarding Personal |
| NENC ICB | North East and North Cumbria Integrated Care Board |
| NPGSV | Newcastle Partnership for Safeguarding and Vulnerability |
| NSAB | Newcastle Safeguarding Adults Board |
| NSCP | Newcastle Safeguarding Children’s Partnership |
| NuTH | Newcastle upon Tyne Hospitals NHS Foundation Trust |
| RCRP | Right Care, Right Person |
| SAR | Safeguarding Adults Review |
| SEG | Strategic Exploitation Group |
| TWFRS | Tyne and Wear Fire and Rescue Service |
| VARM | Vulnerable Adult Risk Management |
| VCS | Voluntary and Community Sector |
| VRU | Violence Reduction Unit |
| YJPB | Youth Justice Partnership Board |

NSAB Strategic Annual Plan 2025-26

| 1. Empowerment: Individuals will be asked what they want as the outcomes from the safeguarding process and these outcomes will directly inform what happens wherever possible. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rationale | Outcome | Action(s) | Lead Officer or Group | Timescale/ Review Date | Status | Progress | Evidence of Achievement |
| Core Performance Indicators (reviewed bi-annually): - People at risk of harm (or their representatives) are asked what they want to happen as a result of a safeguarding adults concern and these views inform the Section 42 enquiry. - People who have substantial difficulty in participating in the safeguarding adults process are represented. Further actions may be identified dependent on data presented. |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | January: |  |
| 1.1 | - Making Safeguarding Personal Toolkit 2020 - CQC guidance on LA assessments. | People who have been involved in safeguarding adults enquiries have the opportunity to feedback on their experience and this informs service development | - Embed feedback questions into safeguarding adults enquiry process. - Undertake appropriate follow up actions, informed by people’s feedback. - Contribute to Safeguarding Adults For Empowerment (SAFE) research being undertaken by Sunderland University exploring older adults’ experiences of the safeguarding adults process. | NSAB Coordinator and Learning and Development Officer NSAB Coordinator | July 2025 September 2025 (update – 3-year research project due to conclude 2027) | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |

| 2. Protection: Individuals will get help and support to report abuse and neglect and get help to take part in the safeguarding process. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Outcome | Action(s) | Lead Officer or Group | Timescale/ Review Date | Status | Progress | Evidence of Achievement |
| 2.1 | - Local partnerships and intelligence. - Cross-partnership working | The NSAB seeks to understand and address factors which may increase vulnerability or risks. | - The NSAB will receive updates where there are areas of joint working to reduce risks and vulnerability e.g. - Public Health (Deaths of Despair) - VRU (Serious Violence Duty) - Domestic abuse (Older People) - Refugee/asylum seeker safeguarding, links to modern slavery. - Student/young adult population | NSAB Chair and NSAB Coordinator | As part of SAB Forward Plan | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |
| 2.2 | - Adult L &N SARs - Adult O SAR DHR - Local DHRs | The NSAB seeks to understand and address factors which may increase vulnerability or risks to adults with care and support needs, in particular safeguarding adults who use drugs and/or alcohol. | - Receive year-end report from Safeguarding Adults Project Manager to understand any outstanding or ongoing priorities and work with Public Health on safeguarding adults who needs are related to their drug/alcohol use. | Safeguarding Adults Project Manager and SAR Committee | May 2025 | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |
| 2.3 | - 2024-25 NSAB Performance Scorecard | The NSAB seeks to understand and address factors which may increase vulnerability or risks to adults with care and support needs, in particular the safeguarding adults at risk of neglect | a) The NSAB will receive further analysis of the data linked to the prevalence of neglect and identify if further actions are required in this area. | NSAB Coordinator | July 2025 | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |
| 2.4 | - Draft Crime and Policing Bill - SAB Manager and Chairs Network Task and Finish Group | The NSAB seeks to understand and address factors which may increase vulnerability or risks to adults with care and support needs, in particular the safeguarding adults at risk of home takeover | - The NSAB contributes to national work on home takeover | Strategic Exploitation Group | January 2026 | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |
| 2.4 | - Whorlton Hall SAR - CQC Closed Cultures Guidance - Carry-over from 2023-24 Strategic Annual Plan | The NSAB is assured that organisational safeguarding processes are robust. | - The NSAB seeks assurance on partner agency approaches to promote and acheive open cultures. | All NSAB members | May 2025 | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |

| 3. Proportionality: Individuals will be confident that professionals will work for their best interests and that professionals will only get involved as much as is needed. |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Outcome | Action(s) | Lead Officer or Group | Timescale/ Review Date | Status | Progress | Evidence of Achievement |  |
| 3.1 | - Scheduled review of Risk Threshold Tool | The NSAB’s Risk Threshold Tool is up-to-date and supports practitioners to take proportionate action. | - Review of NSAB Risk Threshold Tool | Improving Practice Committee | January 2026 | Red Amber Green Complete | May: |  |  |
|  |  |  |  |  |  |  | July: |  |  |
|  |  |  |  |  |  |  | September: |  |  |
|  |  |  |  |  |  |  | November: |  |  |
|  |  |  |  |  |  |  | January: |  |  |
|  |  |  |  |  |  |  | March: |  |  |
|  |  |  |  |  |  |  | July: |  |  |

| 4. Prevention: Individuals will receive clear information about what abuse and neglect is, how to recognise the signs and what they can do to seek help and support. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Outcome | Action(s) | Lead Officer or Group | Timescale/ Review Date |  | Status |  | Progress |  | Evidence of Achievement |  |
| 4.1 | - Care Act 2014 - Core NSAB objective | Ensure key safeguarding messages are promoted using a wide variety of tools and methods. | - Review the NSAB’s Communications Strategy - Increased face-to-face contact with public and adults at risk. - Activities to coincide with Safeguarding Adults Week 2025. | NSAB Coordinator | May 2025 March 2026 November 2025 | Red Amber Green Complete |  | May: |  |  |  |  |  |
|  |  |  |  |  |  |  |  | July: |  |  |  |  |  |
|  |  |  |  |  |  |  |  | September: |  |  |  |  |  |
|  |  |  |  |  |  |  |  | November: |  |  |  |  |  |
|  |  |  |  |  |  |  |  | January: |  |  |  |  |  |
|  |  |  |  |  |  |  |  | March: |  |  |  |  |  |
| 4.2 | - NSAB Self-Assessment Feedback - CQC guidance on LA assessments. | Information about safeguarding adults is co-produced with adults in our communities. | - Review and update of Plain English, Easy Read and Brief Guides. | NSAB Coordinator with support of VCS Reps and their networks | March 2026 |  | Red Amber Green Complete |  | May: |  |  |  |
|  |  |  |  |  |  |  |  |  | July: |  |  |  |
|  |  |  |  |  |  |  |  |  | September: |  |  |  |
|  |  |  |  |  |  |  |  |  | November: |  |  |  |
|  |  |  |  |  |  |  |  |  | January: |  |  |  |
|  |  |  |  |  |  |  |  |  | March: |  |  |  |
| 4.3 | - Care Act 2014. | The workforce in Newcastle is accessing high quality learning and development opportunities appropriate to their role. | a)All partner agencies of the NSAB to provide assurance around their safeguarding adults training (uptake, content, training policy, including any protected time for training). - Seek assurance from commissioners on how training provision within provider services is assessed and monitored. | NSAB Learning and Development Committee | March 2026 May 2025 |  | Red Amber Green Complete |  | May: |  |  |  |
|  |  |  |  |  |  |  |  |  | July: |  |  |  |
|  |  |  |  |  |  |  |  |  | September: |  |  |  |
|  |  |  |  |  |  |  |  |  | November: |  |  |  |
|  |  |  |  |  |  |  |  |  | January: |  |  |  |
|  |  |  |  |  |  |  |  |  | March: |  |  |  |
|  |  |  |  |  |  |  |  |  | July: |  |  |  |
| 4.4 | - Ethnic Minority Needs Assessment (EMNA) - National SAR Analysis - Joint Strategic Needs Assessment (JSNA) | The NSAB understands the diversity of the city and underserved groups, including responses to ethnically minoritised communities. | - The NSAB will compare the EMNA and JSNA with safeguarding data to explore and understand whether there are any barriers to access safeguarding adults support. | NSAB Coordinator & Improving Practice Committee (link with Public Health and HAREF) | March 2026 |  | Red Amber Green Complete |  | May: |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | July: |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | September: |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | November: |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | January: |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  | March: |  |  |  |  |  |

| 5. Partnership: Individuals will be confident that professionals will work together to get the best outcomes for them. |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Outcome | Action(s) | Lead Officer or Group | Timescale/ Review Date | Status | Progress | Evidence of Achievement |
| 5.1 | - Changes in the way partners work (RCPC, NENC ICB) - NSAB Performance Data | The Adult MASH can effectively respond to the sustained volume of safeguarding adults referrals being made. | - The operational model for the Adult MASH will be reviewed to reflect system changes and to enable the MASH to continue to function effectively | NSAB Chair and Statutory Partners | May 2025 | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |
| 5.2 | - NSAB Performance Data | Safeguarding adults referrals received are of a high quality. | - The NSAB will work with partners who currently do not use the multi-agency referral form to request adoption or alignment of single-agency referral forms. | NSAB Coordinator | September 2025 | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |
| 5.3 | - NSAB Self-Assessment | Feedback will be given on all safeguarding adult referrals. | - Newcastle City Council will progress ICT solutions that will provide feedback to referrers. | Newcastle City Council | March 2026 | Red Amber Green Complete | May: |  |
|  |  |  |  |  |  |  | July: |  |
|  |  |  |  |  |  |  | September: |  |
|  |  |  |  |  |  |  | November: |  |
|  |  |  |  |  |  |  | January: |  |
|  |  |  |  |  |  |  | March: |  |
| 5.4 | NSAB Self-Assessment | The NSAB is assured that multi-agency procedures are robust for addressing the challenges of complex cases. | - The NSAB will request information on the use and evaluation of Multi-Agency Risk Management (MARM)/Vulnerable Adult Risk Management (VARM) models. There will be exploration as to whether these add value to the robust existing mechanisms. | NSAB Coordinator | January 2026 | Red Amber Green Complete | May: |  |  |
|  |  |  |  |  |  |  | July: |  |  |
|  |  |  |  |  |  |  | September: |  |  |
|  |  |  |  |  |  |  | November: |  |  |
|  |  |  |  |  |  |  | January: |  |  |
|  |  |  |  |  |  |  | March: |  |  |

| 6. Accountability: Individuals will receive timely help they need from the person or agency best placed to provide it. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rationale |  | Outcome | Action(s) | Lead Officer or Group |  |  | Timescale/ Review Date | Status |  | Progress |  | Evidence of Achievement |  |
| 6.1 | - CQC guidance on LA assessments. | The NSAB and it’s members respond to CQC’s Local Authority Assessment. | - The NSAB will receive a report on the findings of the LA’s CQC assessment on issues which have relevance to the NSAB and undertake any action necessary to learn from their findings to improve and strengthen the NSAB. | Newcastle City Council |  |  | November 2025 | Red Amber Green Complete |  | May: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | July: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | September: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | November: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | January: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | March: |  |  |  |
| 6.2 | - Learning from SARs/DHRs/CSPRs/Other reviews | The NSAB is assured that learning from SARs and other reviews is embedded in practice. | - The NSAB reviews implementation of previous SAR recommendations to ensure they are embedded in practice. - Multi-agency audits are regularly undertaken, and key lines of enquiry take account of learning from SARs. - Good practice cases are shared via the IPC where learning from SARs has been used. - The NSAB will receive updates and learning from fire-related incidents. - The NSAB will develop a toolkit (or similar) which will assist front-line learning, support CPD and encourage reflection on practice. |  | NSAB Coordinator SAR Committee Improving Practice Committee Improving Practice Committee TWFRS Learning and Development Committee | March 2026 March 2026 March 2026 May 2025 March 2026 |  |  | Red Amber Green Complete |  | May: |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | July: |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | September: |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | November: |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | January: |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  | March: |  |  |  |
| 6.3 | - Sharing of Information/Intelligence to enable early intervention and preventative work and also enable escalation where this is required | The NSAB is aware of and can influence relevant regional and national networks or bodies. | - The NSAB will have a standing agenda item on it’s agenda to ensure information and intelligence is shared from relevant regional and national networks. | NSAB Chair and NSAB Coordinator |  |  | At each NSAB meeting | Red Amber Green Complete |  | May: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | July: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | September: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | November: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | January: |  |  |  |
|  |  |  |  |  |  |  |  |  |  | March: |  |  |  |

NSAB Core Business Plan 2025-26

| Business Action(s) |  | Timescale/ Board Meeting | Status | Evidence of Achievement |
| --- | --- | --- | --- | --- |
| 1. | Review and update NSAB Partnership Agreement | - March 2027 | Outstanding On course Complete | Not required within this year’s strategic annual plan. |
| 2. | Review and update NSAB Information Sharing Agreement | - July 2025 | Outstanding On course Complete | . |
| 3. | The NSAB receives performance reports on a bi-annual basis with more frequent exception reporting if concerning patterns or trends are identified. | - July 2025 - January 2026 | Outstanding On course Complete |  |
| 4. | Hold an annual self-assessment / challenge event | - January 2026 | Outstanding On course Complete |  |
| 5. | Production of Newcastle Safeguarding Adult Board Annual Report 2024-25 | - May 2025 (agency submissions) - July 2025 (Draft version for NSAB) - September 2025 (sign-off by NSAB) | Outstanding On course Complete |  |
| 6. | Production of Newcastle Safeguarding Adults Board Strategic Annual Plan 2026-27 | - December 2025(consultation begins) - January 2026 (draft version at NSAB) - March 2026 (sign-off at NSAB) | Outstanding On course Complete |  |
| 7. | Review the membership and terms of reference of the sub-committees. (In addition to any gaps in membership/attendance to be highlighted to NSAB as required via sub-committee reports.) | - March 2025 | Outstanding On course Complete |  |
| 8. | NSAB Risk Register to be updated and agreed by Board members | - Bi-annually | Outstanding On course Complete |  |
| 9. | The NSAB influences national policy and practice based on learning from cases, including use of the National SAR Escalation process and submissions to the National SAR Library. | - As required and opportunities arise. | Outstanding On course Complete |  |
| 10. | The NSAB holds Board Member Development Session, this may be in conjunction with other strategic partnerships (via the NPGSV) | - March 2026 | Outstanding On course Complete | Plan to undertake Board Member Development sessions prior to each NSAB meeting. |